## Sheet1
|  |  |  | America’s Operation Thank You, The Relay In The Sky |  | 40 Flights Under 1 Hour
|  |  |  | Flight Schedule 9/9/20 |  | 41 Flights 1-2 Hours
13 Flights 2-3 Hours
4 Flights 3-4 Hours
DAY | LEG# | DEPARTURE CITY | ARRIVAL | FBO | FLIGHT TIME | TRIP LOGISTICS IN EACH CITY
0 |  | San Diego |  |  |  | 8:30a.m.-9:00-Setup
|  | 1st Ceremony Begins September 23rd | Police Foundation Here | San Diego Airport(SAN) |  | 9-10:30- Kick Off Ceremony with 30 Minute Time Buffer
10:30-11:00- Wrapup
1 | 1 | San Diego (to) | Santa Ana | Atlantic | 41 min | 11:45a.m- Arrival from San Diego Airport
|  | 1st Flight Takeoff Begins September 24th | Police Foundation Here | SNA Airport |  | 11:45 -12:15-Set up
12:15-1:15-Ceremony with 30 Minute Time Buffer
1:15-1:45- Wrapup
1:45-Depart for Burbank
| 2 | Santa Ana (to) | Burbank | MillionAir | 30 min | 2:15p.m.-Arrival
|  | Flight Scehduled for September 24th | Police Foundation Here | BUR Aiport |  | 2:15-2:45-Setup
2:45-3:45-Ceremony with 30 Minute Time Buffer
3:45-4:15-Wrap Up
4:15p.m.-End of Day
2 | 3 | Burbank (to) | Santa Barbara | Atlantic | 1 Hour | 7:30a.m.-Deaprt for Santa Barbara
|  | September 25th | Police Foundation Here | SBA Airport |  | 8:30-Arrival
8:30-9-Setup
9-10:00-Ceremony With 30 Minute Buffer
10-10:30- Wrapup
10:30-Depart for San Jose
| 4 | Santa Barbara (to) | San Jose / San Fran | Signature | 2 Hours | 12:45-Arrive and Set Up
|  | September 25th | Police Foundation Here | SJC Airport |  | 2:45-Wrap Up and Depart for Sacramento
1:15-2:15-Ceremony With 30 Minute Buffer
| 5 | San Jose/San Fran (to) | Sacramento | SAC Jet Center | 45 Minutes | 3:30(Arrival and Setup)-5:30(End of Day)
|  | September 25th | Police Foundation Here | SMF |  | 4:00-5:00-Ceremony with 30 Minute Buffer
3 | 6 | Sacramento (to) | Carson City | Mtn West Aviation | 1 Hour | 7:30a.m.-Depart for Carson City
|  | September 26th | No Police Foundation Here | CXP |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 7 | Carson City | Salem | Salem Aviation Fueling | 3:28 Hours | 2:00(Arrival and Setup)-4:00(End of Day)
|  | September 26th | Police Foundation Here | Mcnary Fld |  | 2:30-3:30-Ceremony with 30 Minute Buffer
DAY | LEG# | DEPARTURE CITY | DEPARTURE | FBO | FLIGHT TIME | TRIP LOGISTICS IN EACH CITY
4 | 8 | Salem | Portland | Atlantic Aviation | 29 Minutes | 8:00-Depart for Portland
|  | September 27th | No Police Foundation Here | PDX |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 9 | Portland | Olympia | Safety In Motion | 52 Minutes | 11:30(Arrival and Setup)-1:30(Departure)
|  | September 27th | No | OLM |  | 12:00-1:00-Ceremony with 30 Minute Buffer
| 10 | Olympia | Seattle | Signature | 25 Minutes | 2:00(Arrival and Setup)-4:00(End of Day)
|  | September 27th | Yes | BFI |  | 2:30-3:30-Ceremony
5 | 11 | Seattle | Boise | Jcksn Jt Ctr | 3.25 hours | 5:30 a.m.-Depart for Boise(We lose an hour in time-zone change)
|  | September 28th | No | BOI |  | 9:30(Arrival and Setup)-11:30(Departure)
10:00-11:00-Ceremony with 30 Minute Buffer
| 12 | Boise | Helena | Exec Air | 2:21 Minutes | 1:30(Arrival and Setup)-3:30(end of Day)
|  | September 28th | Yes | HLN |  | 2:00-3:00-Ceremony with 30 Minute Buffer
6 | 13 | Helena | Billings | Edwards Montana Jet | 1:21 Minutes | 7am-Depart for Billings
|  | September 29th | No | BIL |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 14 | Billings | Salt Lake City | Atlantic | 3:30 Minutes | 2:00(Arrival and Setup)-4:00(End of Day)
|  | September 29th | Yes | SLC |  | 2:30-3:30-Ceremony with 30 Minute Buffer
7 | 15 | Salt Lake City | Las Vegas | Signature | 3:24 Minutes | 6am-Depart for Las Vegas(We gain an hour in time-zone change)
|  | September 30th | Yes | LAS Airport |  | 8:30 a.m.(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 16 | Las Vegas | Phoenix | Cutter | 2:09 Minutes | 12:45(Arrival and Setup)-2:45(End of Day)
|  | September 30th | Yes | PHX |  | 1:15-2:15-Ceremony with 30 Minute Buffer
8 | 17 | Phoenix | Albuquerque | Atlantic | 2:34 Minutes | 5am-Depart for Albuquerque(We lose an hour in time-zone)
|  | October 1st | Yes | ABQ |  | 8:30 a.m.(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 18 | Albuquerque | Santa Fe | Santa Fe Jt Ctr | 30 Minutes | 11:00(Arrival and Setup)-1(Departure)
|  | October 1st | No | SAF |  | 11:30-12:30-Ceremony with 30 Minute Buffer
| 19 | Santa Fe | Colorado Springs | Cutter | 1:52 Minutes | 3:00(Arrival and Setup)-5:00(End of Day)
|  | October 1st | Yes | COS |  | 3:30-4:30-Ceremony with 30 Minute Buffer
9 | 20 | Colorado Springs | Denver | Signature | 33 Minutes | 7:45am-Depart for Denver
|  | October 2nd | Yes | APA |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 21 | Denver | Cheyenne | Legend Aeroserve | 57 Minutes | 11:30(Arrival and Setup)-1:30(Departure)
|  | October 2nd | No | CYS |  | 12:00-1:00-Ceremony with 30 Minute Buffer
| 22 | Cheyenne | Rapid City | West Jet Air Ctr | 1:54 Minutes | 4:00(Arrival and Setup)-6pm(End of Day)
|  | October 2nd | No | RAP Airport |  | 4:00-5:00-Ceremony with 30 Minute Buffer
DAY | LEG# | DEPARTURE CITY | ARRIVAL CITY | FBO | FLIGHT TIME | TRIP LOGISTICS IN EACH CITY
10 | 23 | Rapid City | Bismarck | Aero Ctr | 1:54 Minutes | 5:30am-Depart for Bismarck(We lose an hour in time-zone)
|  | October 3rd | No | BIS |  | 8:30(Arrival and Setup)-10:30-Length of Stay(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 24 | Bismarck | Pierre | Mustang Aviation | 1:27 Minutes | 12:30(Arrival and Setup)-2:30(Departure)
|  | October 3rd | No | PIR |  | 1:00-2:00-Ceremony with 30 Minute Buffer
| 25 | Pierre | Sioux Falls | Maverick Air Ctr | 1:28 Minutes | 4:00(Arrival and Setup)-6:00(End of Day)
|  | October 3rd | No | FSD |  | 4:30-5:30-Ceremony with 30 Minute Buffer
11 | 26 | Sioux Falls | Omaha | Tac Air | 1:22 Minutes | 7am-Depart for Omaha
|  | October 4th | Yes | OMA |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 27 | Omaha | Lincoln | Silver Hawk | 36 Minutes | 11:00(Arrival and Setup)-1:00(Departure)
|  | October 4th | No | LNK |  | 11:30-12:30-Ceremony with 30 Minute Buffer
| 28 | Lincoln | Kansas City | Signature | 1:22 Minutes | 2:30(Arrival and Setup)-4:30(End of Day)
|  | October 4th | Yes | MKC |  | 3:00-4:00-Ceremony with 30 Minute Buffer
12 | 29 | Kansas City | Topeka | Million Air | 37 Minutes | 7:45am-Depart for Topeka
|  | October 5th | No | FOE |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 30 | Topeka | Wichita | Signature | 1:18 Minutes | 12:00(Arrival and Setup)-2:00(Departure)
|  | October 5th | Yes | ICT |  | 12:30-1:30-Ceremony with 30 Minute Buffer
| 31 | Wichita | Tulsa | Atlantic | 1:10 Minutes | 3:15(Arrival and Setup)-5:15(End of Day)
|  | October 5th | Yes | TUL |  | 3:45-4:45-Ceremony with 30 Minute Buffer
13 | 32 | Tulsa | Oklahoma City | Atlanitc | 1:05 Minutes | 7:20am-Depart for Oklahoma
|  | October 6th | No | OKC |  | 8:30(Arrival and Setup)-10:30(Departure)
9am-10:00-Ceremony with 30 Minute Buffer
| 33 | Oklahoma City | Dallas Fort Worth | Signature | 1:43 Minutes | 12:30(Arrival and Setup)-2:30(End of Day)
|  | October 6th | Yes | DAL |  | 1:00-2:00-Ceremony with 30 Minute Buffer
14 | 34 | Dallas/Fort Worth | Austin | Signature | 1:51 Minutes | 6:30am-Depart for Austin
|  | October 7th | Yes | AUS |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 35 | Austin | San Antonio | Signature | 38 Minutes | 11:15(Arrival and Setup)-1:15(Departure)
|  | October 7th | No | SAT |  | 11:45-12:45-Ceremony with 30 Minute Buffer
| 36 | San Antonio | Houston | Signature | 1:40 Minutes | 3:15(Arrival and Setup)-5:15(End of Day)
|  | October 7th | Yes | HOU |  | 3:45-4:45-Ceremony with 30 Minute Buffer
15 | 37 | Houston | Shrevport | Tubreax Aviation | 1:45 Minutes | 6:45am-Depart for Shrevport
|  | October 8th | Yes | DTN |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
DAY | LEG# | DEPARTURE CITY | ARRIVAL CITY | FBO | FLIGHT TIME | TRIP LOGISTICS IN EACH CITY
| 38 | Shrevport | Little Rock | TACAir | 1:25 Minutes | 12:00(Arrival and Setup)-2:00(Departure)
|  | October 8th | Yes | LIT |  | 12:00-1:00-Ceremony with 30 Minute Buffer
| 39 | Little Rock | Jefferson City | Jefferson City Flying | 2:09 Minutes | 4:15(Arrival and Setup)-6:15(End of Day)
|  | October 8th | No | JEF |  | 4:45-5:45-Ceremony with 30 Minute Buffer
16 | 40 | Jefferson City | Des Moines | Signature | 2:01 Minutes | 6:30am-Depart for Des Moines
|  | October 9th | Yes | DSM Airport |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 41 | Des Moines | Minneapolis/Saint Paul | Signature | 1:58 Minutes | 12:30(Arrival and Setup)-2:30(End of Day)
|  | October 9th | Yes | STP |  | 1:00-2:00-Ceremony with 30 Minute Buffer
17 | 42 | Minneapolis/Saint Paul | Osh Kosh | Basler Flt Serv | 1:52 Minutes | 6:30am-Depart for Osh Kosh
|  | October 10th | No | OSH |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 43 | Osh Kosh | Madison | Wisconsin Aviation | 41 Minutes | 11:15(Arrival and Setup)-1:15(Departure)
|  | October 10th | Yes | MSN |  | 11:45-12:45-Ceremony with 30 Minute Buffer
| 44 | Madison | Milwaukee | Signature | 40 Minutes | 2:00(Arrival and Setup)-4:00(End of Day)
|  | October 10th | Yes | MKE |  | 2:30-3:30-Ceremony with 30 Minute Buffer
18 | 45 | Milwaukke | Chicago | Atlantic | 50 Minutes | 7:30am-Depart for Chicago
|  | October 11th | Yes | MDW |  | 8:30(Arrival and Setup)-10:30(Departure)
9am-10:00-Ceremony with 30 Minute Buffer
| 46 | Chicago | Springfield | Stellar Av | 1:20 Minutes | 12:00(Arrival and Setup)-2:00(Departure)
|  | October 11th | No | SPI |  | 12:30-1:30-Ceremony with 30 Minute Buffer
| 47 | Springfield | St.Louis | Signature | 46 Minutes | 2:45(Arrival and Setup)-4:45(End of Day)
|  | October 11th | Yes | STL |  | 3:15-4:15-Ceremony with 30 Minute Buffer
19 | 48 | St.Louis | Memphis | Signature | 2:08 Minutes | 6:15am-Depart for Memphis
|  | October 12th | Yes | MEM |  | 8:30(Arrive and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 49 | Memphis | Jackson | Atlanitc | 1:30 Minutes | 12(Arrival and Setup)-2:00(End of Day)
|  | October 12th | No | JAN |  | 12:30-1:30-Ceremony with 30 Minute Buffer
20 | 50 | Jackson | Baton Rouge | Signature | 1:20 Minutes | 7am-Depart for Baton Rouge
|  | October 13th | Yes | BTR |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 51 | Baton Rouge | New Orleans | Signature | 38 Minutes | 11:00(Arrival and Setup)-1:00(Departure)
|  | October 13th | Yes | NEW |  | 11:30-12:30-Ceremony with 30 Minute Buffer
| 52 | New Orleans | Mobile | Signature | 1:10 Minutes | 2:15(Arrival and Setup)-4:15(End of Day)
|  | October 13th | Yes | BFM |  | 2:45-3:45-Ceremony
DAY | LEG# | DEPARTURE CITY | ARRIVAL CITY | FBO | FLIGHT TIME | TRIP LOGISTICS IN EACH CITY
21 | 53 | Mobile | Montgomery | Montgomery Av | 1:15 Minutes | 7:15am-Depart for Montgomery
|  | October 14th | Yes | MGM |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 54 | Montgomery | Birmingham | Atlantic | 50 Minutes | 11:30(Arrival and Setup)-1:30(Departure)
|  | October 14th | Yes | BHM Airport |  | 12:00-1:00-Ceremony with 30 Minute Buffer
| 55 | Birmingham | Nashville | Atlanitc | 1:32 Minutes | 3:00(Arrival and Setup)-5:00(End of Day)
|  | October 14th | No | BNA |  | 3:30-4:30-Ceremony with 30 Minute Buffer
22 | 56 | Nashville | Louisville | Atlanitc | 1:16 Minutes | 6:15am-Depart for Louisville(We lose an hour in time-zone)
|  | October 15th | Yes | SDF |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 57 | Louisville | Frankfort | Capitol City Arpt | 26 Minutes | 11(Arrival and Setup)-1:00(Departure)
|  | October 15th | No | FFT |  | 11:30-12:30-Ceremony with 30 Minute Buffer
| 58 | Frankfort | Cincinnati | Signature | 37 Minutes | 1:45(Arrival and Setup)-3:45(End of Day)
|  | October 15th | Yes | LUK |  | 2:15-3:15-Ceremony with 30 Minute Buffer
23 | 59 | Cincinnati | Indianapolis | Signature | 1:06 Minutes | 7:15am-Depart for Indianapolis
|  | October 16th | No | IND |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 60 | Indianapolis | Lansing | Avflight | 1:53 Minutes | 12:30(Arrival and Setup)-2:30(Departure)
|  | October 16th | No | LAN |  | 1-2:00-Ceremony with 30 Minute Buffer
| 61 | Lansing | Detroit | Signature | 40 Minutes | 3:15(Arrival and Setup)-5:15(End of Day)
|  | October 16th | Yes | DTW |  | 3:45-4:45-Ceremony with 30 Minute Buffer
24 | 62 | Detroit | Columbus | Signature | 1:17 Minutes | 7:15am-Depart for Columbus
|  | October 17th | Yes | CMH |  | 8:30(Arrival and Setup)-10:30(Departure)
9-10am-Ceremony with 30 Minute Buffer
| 63 | Columbus | Charleston | Cap Jet Center | 1:54 Minutes | 12:30(Arrival and Setup)-2:30(Departure)
|  | October 17th | No | CRW |  | 1-2:00-Ceremony with 30 Minute Buffer
| 64 | Charleston | Knoxville | TacAir | 2:40 Minutes | 4:30(Arrival and Setup)-6:30(End of Day)
|  | October 17th | No | TYS |  | 5:00-6:00-Ceremony
25 | 65 | Knoxville | Atlanta | Signature | 1:09 Minutes | 7:15am-Depart for Atlanta
|  | October 18th | Yes | PDK |  | 8:30(Arrival and Setup)-10:30(Departure)
9-10:00-Ceremony with 30 Minute Buffer
| 66 | Atlanta | Tallahassee | MillionAir | 1:58 Minutes | 12:30(Arrival and Setup)-2:30(End of Day)
|  | October 18th | No | TLH |  | 1-2:00-Ceremony with 30 Minute Buffer
26 | 67 | Tallahassee | Tampa | Signature | 1:38 Minutes | 7am-Depart for Tampa
|  | October 19th | Yes | TPA |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 68 | Tampa | Key West | Signature | 2:00 Minutes | 12:30(Arrival and Setup)-2:30(Departure)
DAY | LEG# | DEPARTURE CITY | ARRIVAL CITY | FBO | FLIGHT TIME | TRIP LOGISTICS IN EACH CITY
|  | October 19th | No | EYW |  | 1-2:00-Ceremony with 30 Minute Buffer
| 69 | Key West | Miami | Signature | 1:07 Minutes | 3:45(Arrival and Setup)-5:45(End of Day)
|  | October 19th | Yes | MIA |  | 4:15-5:15-Ceremony with 30 Minute Buffer
27 | 70 | Miami | Orlando | Signature | 1:40 Minutes | 6:30am-Depart for Orlando
|  | October 20th | Yes | MCO |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 71 | Orlando | Jacksonville | Signature | 1:18 Minutes | 12:00(Arrival and Setup)-2:00(End of Day)
|  | October 20th | No | JAX |  | 12:30-1:30-Ceremony with 30 Minute Buffer
28 | 72 | Jacksonville | Savannah | Signature | 1:08 Minutes | 7:15am-Depart for Savannah
|  | October 21st | No | SAV Airport |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 73 | Savannah | Charleston | Atlantic | 44 Minutes | 11:15(Arrival and Setup)-1:15(Departure)
|  | October 21st | No | JZI |  | 11:45-12:45-Ceremony with 30 Minute Buffer
| 74 | Charleston | Columbia | Columbia Aviation | 1:02 Minutes | 2:15(Arrival and Setup)-4:15(End of Day)
|  | October 21st | Yes | CAE |  | 2:45-3:45-Ceremony with 30 Minute Buffer
29 | 75 | Columbia | Charlotte | Wilson Air Ctr | 50 Minutes | 7:30am-Depart for Charlotte
|  | October 22nd | Yes | CLT |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 76 | Charlotte | Raleigh | Signature | 1:06 Minutes | 11:45(Arrival and Setup)-1:45(Departure)
|  | October 22nd | No | RDU |  | 12:15-1:15-Ceremony with 30 Minute Buffer
| 77 | Raleigh | Virgina Beach | Signature | 1:19 Minutes | 3:15(Arrival and Setup)-5:15(End of Day)
|  | October 22nd | Yes | ORF |  | 3:45-4:45-Ceremony with 30 Minute Buffer
30 | 78 | Virginia Beach | Richmond | MillionAir | 44 Minutes | 7:45am-Depart for Richmond
|  | October 23rd | Yes | RIC Airport |  | 8:30(Arrival and Setup)-10:30(Departure)
| 79 | Richmond | Pittsburgh | Atlanitc | 2:30 Minutes | 1(Arrival and Setup)-3:00(End of Day)
|  | October 23rd | Yes | PIT Airport |  | 1:30-2:30-Ceremony with 30 Minute Buffer
31 | 80 | Pittsburgh | Cleaveland | Signature | 1:02 Minutes | 7:30am-Depart for Cleaveland
|  | October 24th | Yes | BKL |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 81 | Cleaveland | Buffalo | Prior Av Serv | 1:28 Minutes | 12(Arrival and Setup)-2:00(End of Day)
|  | October 24th | No | BUF |  | 12:30-1:30-Ceremony with 30 Minute Buffer
32 | 82 | Buffalo | Albany | MillionAir | 2:17 Minutes | 6am-Depart for Albany
|  | October 25th | No | ALB |  | 8:30(Arrival and Setup)-10:30(Departure)
9am-10:00-Ceremony with 30 Minute Buffer
| 83 | Albany | Montpelier | VT Flying Serv | 1:01 Minutes | 11:45(Arrival and Setup)-1:45(Departure)
DAY | LEG# | DEPARTURE CITY | ARRIVAL CITY | FBO | FLIGHT TIME | TRIP LOGISTICS IN EACH CITY
|  | October 25th | No | MPV |  | 12:15-1:15-Ceremony with 30 Minute Buffer
| 84 | Montpelier | Augusta | Maine Instrument Flt | 1:08 Minutes | 3:00(Arrival and Setup)-5:00(End of Day)
|  | October 25th | No | AUG |  | 3:30-4:30-Ceremony with 30 Minute Buffer
33 | 85 | Augusta | Portland | Mac Jet | 32 Minutes | 8am-Depart for Portland
|  | October 26th | No | PWM |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 86 | Portland | Concord | Concord Av Serv | 39 Minutes | 11:15(Arrival and Setup)-1:15(Departure)
|  | October 26th | Yes | CON |  | 11:45-12:45-Ceremony with 30 Minute Buffer
| 87 | Concord | Boston | Signature | 55 Minutes | 2:00(Arrival and Setup)-4:00(End of Day)
|  | October 26th | Yes | BOS |  | 2:30-3:30-Ceremony with 30 Minute Buffer
34 | 88 | Boston | Providence | Northstar Av | 30 Minutes | 8am-Depart for Providence
|  | October 27th | No | PVD |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 89 | Providence | Hartford | Hartford Jet Ctr | 55 Minutes | 11:15(Arrival and Setup)-1:15(Departure)
|  | October 27th | No | HFD AIrport |  | 11:45-12:45-Ceremony with 30 Minute Buffer
35 | 90 | Hartford | New York City | Signature | 54 Minutes | 7:30am-Depart for New York
|  | October 28th | Yes | TEB |  | 8:30(Arrival and Setup)-10:30(Departure)
9-10:00-Ceremony with 30 Minute Buffer
| 91 | New York City | Newark | Signature | 9 Minutes | 10:45(Arrival and Setup)-12:45(Departure)
|  | October 28th | Yes | EWR |  | 11:15-12:15-Ceremony with 30 Minute Buffer
| 92 | Newark | Trenton | Signature | 28 Minutes | 1:15(Arrival and Setup)-3:15(End of Day)
|  | October 28th | Yes | TTN |  | 1:45-2:45-Ceremony with 30 Minute Buffer
36 | 93 | Trenton | Philadelphia | Atlanitc | 13 Minutes | 8:15-Depart for Philadelphia
|  | October 29th | Yes | PHC |  | 8:30(Arrival and Setup)-10:30(Departure)
9:00-10:00-Ceremony with 30 Minute Buffer
| 94 | Philadelphia | Harrisburg | Skyport Av | 1:00 hour | 11:30(Arrival and Setup)-1:30(Departure)
|  | October 29th | No | CXY |  | 12:00-1-Ceremony with 30 Minute Buffer
| 95 | Harrisburg | Dover | DRB Authority | 50 Minutes | 11:30(Arrival and Setup)-1:30(Departure)
|  | October 29th | No | 33N |  | 12:00-1:00-Ceremony with 30 Minute Buffer
| 96 | Dover | Baltimore | Signature | 30 Minutes | 2:15(Arrival and Setup)-4:15(Departure)
|  | October 29th | No | BWI |  | 2:45-3:45-Ceremony with 30 Minute Buffer
| 97 | Baltimore | Washington DC | Signature | 20 Minutes | 4:40(Arrive In Washington)-6:40p.m.(Final End of Day)
|  | October 29th | Yes | DCA Airport |  | 5:15-6:15p.m.-Ceremony with 30 Minute Buffer